## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | PHP Error accompanied with error prompt, which is design to inform the user about the error. | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing.
2 | 1 | Bootstrap (Upload) | Screen is empty, when uploading data.zip files with missing mandatory CSV files | High | 10 |  | Stop current development and resolved the bug immediately. Project manager reschedules the project.
3 | 1 | Bootstrap (Upload) | Error at the following CSV file: Course.csv - AT Row 2 - UNDER Exam Date Column with (empty Exam Date) which a cause PHP error. | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
4 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 3 - UNDER Exam Date Column with (Alphanumeric exam date) - Alphanumeric exam date will cause PHP error. | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
5 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 4 - UNDER Exam Date Column with (Exam Date space) - Date with space will cause PHP error. | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
6 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 5 - UNDER Exam Date Column with (Date with extra numbers) - Date with extra numbers will cause PHP error | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
7 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 15 - UNDER Title Column with (empty title) - data could pass through, when field should not allow empty variables | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
8 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 16 - UNDER Description Column with (Empty description) - deleted description will cause PHP error | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
9 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 18 - UNDER Course Column with (Empty course) - Data could pass through, when field should not allow empty variables | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
10 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 22 - UNDER School Column with (Empty School) - Date could pass through, when field should not allow empty variables | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
11 | 2 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 23 - UNDER Exam Date Column with (Alphanumeric)-Alphanumeric exam date will give a PHP error | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
12 | 2 | Bootstrap (Upload) | When course.csv has all empty fields for all columns in a row, it only shows "blank course" . The line number does not increase, causing subsequent errors to have a wrong line number (smaller by 1) | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User) | PHP Error accompanied with error prompt, which is design to inform the user about the error. | Unresolved | 2019-09-30 |  | Sheng Qin & Vittorio
2 | 1 | Bootstrap (Upload) | Screen is empty, when uploading data.zip files with missing mandatory CSV files | Unresolved | 2019-10-01 |  | Sheng Qin & Vittorio
3 | 1 | Bootstrap (Upload) | Error at the following CSV file: Course.csv - AT Row 2 - UNDER Exam Date Column with (empty Exam Date) which a cause PHP error. | Resolved | 2019-10-01 | 2019-10-16 | Sheng Qin & Vittorio
4 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 3 - UNDER Exam Date Column with (Alphanumeric exam date) - Alphanumeric exam date will cause PHP error. | Resolved | 2019-10-01 | 2019-10-16 | Sheng Qin & Vittorio
5 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 4 - UNDER Exam Date Column with (Exam Date space) - Date with space will cause PHP error. | Resolved | 2019-10-01 | 2019-10-16 | Sheng Qin & Vittorio
6 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 5 - UNDER Exam Date Column with (Date with extra numbers) - Date with extra numbers will cause PHP error | Resolved | 2019-10-01 | 2019-10-16 | Sheng Qin & Vittorio
7 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 15 - UNDER Title Column with (empty title) - data could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-16 | Brendon & DaEun
8 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 16 - UNDER Description Column with (Empty description) - deleted description will cause PHP error | Resolved | 2019-10-01 | 2019-10-16 | Brendon & DaEun
9 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 18 - UNDER Course Column with (Empty course) - Data could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-16 | Brendon & DaEun
10 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 22 - UNDER School Column with (Empty School) - Date could pass through, when field should not allow empty variables | Unresolved | 2019-10-01 | 2019-10-16 | Brendon & DaEun
11 | 2 | Bootstrap (Upload) | This page isn’t working. 18.216.225.229 is currently unable to handle this request. A row with duplicate course AND section in section.csv will result in this error. | Resolved | 2019-10-16 | 2019-10-16 | Sheng Qin & DaEun
12 | 2 | Bootstrap (Upload) | When course.csv has all empty fields for all columns in a row, it only shows "blank course" . The line number does not increase, causing subsequent errors to have a wrong line number (smaller by 1) | Unresolved | 2019-10-16
13 | 3 | Bootstrap (Upload) | Blank screen appear after bootstrapping for the first time. Need to relogin again for the 'Round Open/Close' option to show. | Unresolved | 2019-10-31
14 | 3 | Bootstrap (Upload) | After bootstrapping, bid amount will always end up as whole number instead of a float value | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Sheng Qin
15 | 3 | Add Bid | There is a frontend error where it does not allow users to input decimal places for the 'Add Bid' page | Resolved | 2019-10-31 | 2019-11-02 | Vittorio & DaEun
16 | 3 | Bootstrap (Upload) | Add bids instead of update bids when userid and current course exists, causing a exam timetable clash. Should be bid update instead. | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Sheng Qin
17 | 3 | JSON - Bootstrap | Error field message not sorted | Unresolved | 2019-10-31