## Slide 1: SPM
Sheng Qin, Brendon, Vittorio, DaEun, Matthew

## Slide 2: Schedule & Functionality

## Slide 3: Project Timeline (Planned)
Week 6 - 7
Iteration 1 (PM Review)
Deliverables:
Login.php
DAO files
Addbid.php
DropBid.php
PM Review slides
Create Design Bootstrap 4 file
Iteration 2 (Application Demo)
Deliverables: - biosdb.sql - bootstrap-process.php - JSON (Bootstrap output) - JSON (Student output) - JSON (Admin output) - Admin.php - Application Demo slides Validations for Add Bids Drop Bid fixes
Week 8 - 9
Iteration 3 (UAT)
Deliverables: -clearBidOne-process.php -clearBidTwo-process.php -dropSection.php -Any additional backend files Preparation of manual and JSON test cases (Product completed)
Week 10 - 11
Iteration 4 (Application Finalization and Debugging)
Deliverables: - Any additional JSON pages Resolve bug fixes found in the UAT
Run test cases and bug fix accordingly
Week 12 - 13
Iteration 5 (Submission)
Deliverables: - Final slides for presentation
Week 14

## Slide 4: Project Timeline (Actual)
Week 6 - 7
Iteration 1 (PM Review)
Deliverables:
Login.php
DAO files
Addbid.php
DropBid.php
PM Review slides
Implement Bootstrap 4
Update of designs & Wireframes
Create user test cases
Iteration 2 (Application Demo)
Deliverables: - biosdb.sql - bootstrap-process.php - JSON (Bootstrap output) - JSON (Student output) - JSON (Admin output) - Admin.php - Application Demo slides - Dropbid.php - Update navigation bar - Run test cases -Validations for Add Bids -Drop Bid fixes
Week 8 - 9
Iteration 3 (UAT)
Deliverables: -clearBidOne-process.php -clearBidTwo-process.php -dropSection.php -Any additional backend files -JSON additional pages (bid-dump.php, delete-bid.php...etc) -Protect.php -Preparation of manual and JSON test cases - Update scheduling (Product completed)
Week 10 - 11
Iteration 4 (Application Finalization and Debugging)
Deliverables: - Any additional JSON pages Resolve bugs found in the UAT - Resolve bugs from the previous iterations - Add further validations for “addBids.php” -Run test cases and bug fix accordingly
Week 12 - 13
Iteration 5 (Submission)
Deliverables: - Final slides for presentation Resolve bugs found in the UAT Create and run additional manual/automatic test cases
(Product completed)
Week 14

## Slide 5: Breakdown of work
 | Programming tasks | Non-Programming tasks
Members | Code pages as allocated by the PM Bug Searching and Fixing | Understand logic & architecture of the website Voice any concerns of current plan
Project Manager | Only applicable in Week 8 | DU Scheduling Minutes upload

## Slide 6: Functionalities
No functionalities dropped
Filter functionality implemented for the add bid page
No PHP frameworks or external libraries used
Used Bootstrap 4 for better UI/UX

## Slide 7: Task Allocation
Name | Hours Spent | Percentage (%)
Sheng Qin | 113.48 | 18.6
Matthew | 114.81 | 18.8
Vittorio | 137.53 | 22.6
Da Eun | 109.30 | 17.9
Brendon | 134.98 | 22.1

## Slide 8: Scheduling Complications
Lack of communication
Regularity of Git pushes (DU)
Accidentally reverting Git for minutes
Hard to break down tasks. Lack of understanding of the level of detail required

## Slide 9: Bug Metrics

## Slide 10: Resolving bugs: A visual representation
Iteration | Number of bugs detected | Rescheduling required?
1 | 10 | Yes
2 | 17 | Yes
3 | 19 | Yes
4 | 15 | Yes
5 | 17 | Yes

## Slide 11: Resolving Bugs
Bug searching and then debugging
Bug Metric was used to:
  Prioritize work
  Communication within team
  Urgency

## Slide 12: High Priority Bug: Example
Bug on the admin page: Cause an PHP error upon bootstrap upload.
Team’s protocol in addressing bugs
  If founding pair unable to debug: other team will recreated in their environment and attempt fix.
  If unable, debug together as a group

## Slide 13: Bug Metric: Challenges
Bugs were difficult to document
Debugged first, then documented
Initial confusion between the bug metric and the bug log
Requires discipline to add to the bug metric & remove it

## Slide 14: Usage of Git

## Slide 16: Spread of commits

## Slide 17: Reflections

## Slide 19: It wasn’t all smooth sailing...
Different priorities:
  Frontend vs Backend
  Looking at the big picture vs focusing on our current problems
Pair programming
Variable naming

## Slide 20: Lessons Learnt - Traits of a good PM
Be meticulous with your scheduling
Try to have good communication with your team
Be committed to your DU and scheduling

## Slide 21: Thank you!