## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | PHP Error accompanied with error prompt, which is design to inform the user about the error. | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing.
2 | 1 | Bootstrap (Upload) | Error at the following CSV file: Course.csv - AT Row 2 - UNDER Exam Date Column with (empty Exam Date) which a cause PHP error. | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
3 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 3 - UNDER Exam Date Column with (Alphanumeric exam date) - Alphanumeric exam date will cause PHP error. | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
4 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 4 - UNDER Exam Date Column with (Exam Date space) - Date with space will cause PHP error. | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
5 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 5 - UNDER Exam Date Column with (Date with extra numbers) - Date with extra numbers will cause PHP error | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
6 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 15 - UNDER Title Column with (empty title) - data could pass through, when field should not allow empty variables | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
7 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 16 - UNDER Description Column with (Empty description) - deleted description will cause PHP error | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
8 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 18 - UNDER Course Column with (Empty course) - Data could pass through, when field should not allow empty variables | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
9 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 22 - UNDER School Column with (Empty School) - Date could pass through, when field should not allow empty variables | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
10 | 2 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 23 - UNDER Exam Date Column with (Alphanumeric)-Alphanumeric exam date will give a PHP error | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
11 | 2 | Bootstrap (Upload) | When course.csv has all empty fields for all columns in a row, it only shows "blank course" . The line number does not increase, causing subsequent errors to have a wrong line number (smaller by 1) | Low | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User) | PHP Error accompanied with error prompt, which is design to inform the user about the error. | Resolved | 2019-09-30 | 2019-10-01 | Sheng Qin & Vittorio
2 | 1 | Bootstrap (Upload) | Error at the following CSV file: Course.csv - AT Row 2 - UNDER Exam Date Column with (empty Exam Date) which a cause PHP error. | Resolved | 2019-10-01 | 2019-10-16 | Sheng Qin & Vittorio
3 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 3 - UNDER Exam Date Column with (Alphanumeric exam date) - Alphanumeric exam date will cause PHP error. | Resolved | 2019-10-01 | 2019-10-16 | Sheng Qin & Vittorio
4 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 4 - UNDER Exam Date Column with (Exam Date space) - Date with space will cause PHP error. | Resolved | 2019-10-01 | 2019-10-16 | Sheng Qin & Vittorio
5 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 5 - UNDER Exam Date Column with (Date with extra numbers) - Date with extra numbers will cause PHP error | Resolved | 2019-10-01 | 2019-10-16 | Sheng Qin & Vittorio
6 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 15 - UNDER Title Column with (empty title) - data could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-16 | Brendon & DaEun
7 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 16 - UNDER Description Column with (Empty description) - deleted description will cause PHP error | Resolved | 2019-10-01 | 2019-10-16 | Brendon & DaEun
8 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 18 - UNDER Course Column with (Empty course) - Data could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-16 | Brendon & DaEun
9 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 22 - UNDER School Column with (Empty School) - Date could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-16 | Brendon & DaEun
10 | 2 | Bootstrap (Upload) | This page isn’t working. 18.216.225.229 is currently unable to handle this request. A row with duplicate course AND section in section.csv will result in this error. | Resolved | 2019-10-16 | 2019-10-16 | Sheng Qin & DaEun
11 | 2 | Bootstrap (Upload) | When course.csv has all empty fields for all columns in a row, it only shows "blank course" . The line number does not increase, causing subsequent errors to have a wrong line number (smaller by 1) | Resolved | 2019-10-16 | 2019-10-20 | Sheng Qin & Brendon
12 | 3 | Bootstrap (Upload) | Blank screen appear after bootstrapping for the first time. Need to relogin again for the 'Round Open/Close' option to show. | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Sheng Qin
13 | 3 | Bootstrap (Upload) | After bootstrapping, bid amount will always end up as whole number instead of a float value | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Sheng Qin
14 | 3 | Add Bid | There is a frontend error where it does not allow users to input decimal places for the 'Add Bid' page | Resolved | 2019-10-31 | 2019-11-02 | Vittorio & DaEun
15 | 3 | Bootstrap (Upload) | Add bids instead of update bids when userid and current course exists, causing a exam timetable clash. Should be bid update instead. | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Sheng Qin
16 | 3 | JSON - Bootstrap | Error field message not sorted | Unresolved | 2019-10-31
17 | 3 | Add Bid | There is an error caused by non-standardized variable names | Resolved | 2019-11-07 | 2019-11-07 | Matthew & Sheng Qin
18 | 3 | Add Bid | Vacancy does not change if a bid is dropped | Resolved | 2019-11-07 | 2019-11-07 | Matthew & Sheng Qin
19 | 3 | Add Bid | No validation if the vacancy is already at 0 - bid goes through even though there is no vacancy | Resolved | 2019-11-07 | 2019-11-07 | Matthew & Sheng Qin
20 | 3 | Add Bid | No validation if you bid for two sections of the same course at the same time | Resolved | 2019-11-09 | 2019-11-09 | Matthew & Sheng Qin
21 | 3 | Add Bid | No validation if you bid for two sections of the same course in separate bids | Resolved | 2019-11-09 | 2019-11-11 | Matthew & Sheng Qin
22 | 3 | Add Bid | Should be able to bid even when vacancy is temporarily 0 during round 2. Shouldn't allow bids if round 1 ends, and vacancy is 0 | Resolved | 2019-11-09 | 2019-11-09 | Vittorio & DaEun
23 | 3 | Drop Bid | You can drop a bid once the window is closed. You should only be able to drop bids during active rounds | Resolved | 2019-11-11 | 2019-11-11 | Matthew & Sheng Qin
24 | 3 | Drop Section | You can drop a section once the window is closed. You should only be able to drop sections during active rounds | Resolved | 2019-11-11 | 2019-11-11 | Matthew & Sheng Qin
25 | 4 | Bootstrap | Does not show success message or how many lines have been processed | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
26 | 4 | Bootstrap | Non-consistent bid amounts when clicking on landing page and add bid page | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
27 | 4 | Landing page | Not being able to show status result of bids after round 1 | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
28 | 4 | Drop Section | Money should be refunded when a section is dropped | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
29 | 4 | Drop Bid round 2 | When vacancy reaches max limit, those that were out-bid would causes all other bids status to fail. | Resolved | 14/11/2019 | 14/11/2019 | Brendon & Vittorio
30 | 4 | Admin Page | Exclamation mark appears if no file is imported on the admin page
31 | 4 | Admin Page | Error if no file is imported on the bootstrap | Resolved | 16/11/2019 | 16/11/2019 | Matthew & DaEun
32 | 4 | Add Bid page | Bid amount can exceed amount in wallet | Unresolved | 16/11/2019