## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | PHP Error accompanied with error prompt, which is design to inform the user about the error. | Low impact | 1 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Login (Admin) | Password accepted for both capitalised and non capitalised variations | Low impact | 1
3 | 1 | Bootstrap (Upload) | Error at the following CSV file: Course.csv - AT Row 2 - UNDER Exam Date Column with (empty Exam Date) which a cause PHP error. | Low impact | 1
4 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 3 - UNDER Exam Date Column with (Alphanumeric exam date) - Alphanumeric exam date will cause PHP error. | Low impact | 1
5 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 4 - UNDER Exam Date Column with (Exam Date space) - Date with space will cause PHP error. | Low impact | 1
6 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 5 - UNDER Exam Date Column with (Date with extra numbers) - Date with extra numbers will cause PHP error | Low impact | 1
7 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 15 - UNDER Title Column with (empty title) - data could pass through, when field should not allow empty variables | Low impact | 1
8 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 16 - UNDER Description Column with (Empty description) - deleted description will cause PHP error | Low impact | 1
9 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 18 - UNDER Course Column with (Empty course) - Data could pass through, when field should not allow empty variables | Low impact | 1
10 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 22 - UNDER School Column with (Empty School) - Date could pass through, when field should not allow empty variables | Low impact | 1
11 | 2 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 23 - UNDER Exam Date Column with (Alphanumeric)-Alphanumeric exam date will give a PHP error | Low impact | 1 | 93 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
12 | 2 | Bootstrap (Upload) | When course.csv has all empty fields for all columns in a row, it only shows "blank course" . The line number does not increase, causing subsequent errors to have a wrong line number (smaller by 1) | Low impact | 1
13 | 2 | Bootstrap (Upload) | Bootstrap error results in PHP error caused in the database due to incorrect column type | Critical Impact | 10
14 | 2 | Bootstrap (Upload) | Bid.csv cause PHP error upon bootstrap upload | Critical Impact | 10
15 | 2 | Drop bids | Dropped bids were not removed | Low impact | 1
16 | 2 | Landing page | Current bid is displayed as php error | Low impact | 5
17 | 2 | Add Bids | Above 5 bids cause PHP error | Low impact | 3
18 | 2 | Admin Page | Upon logging into admin page, PHP error is produce and unable to bootstrap. | Critical Impact | 13
19 | 2 | Rounds clearing logic | Upon closing "round 1 opening" after bootstrap, cause PHP error and does not reflect on rounds in landing page. | High Impact | 5
20 | 2 | Landing page | User unable to determine which round they are in | Low impact | 1
21 | 2 | Landing page | User unable to determine whether the round is open or not | Low impact | 1
22 | 2 | Landing page / add bids | Bid value does not get deducted upon adding bids | High Impact | 5
23 | 2 | Add bids | Bid value can become a negative value | High Impact | 7
24 | 2 | Landing Page / bids | Trying to show the e$ produce PHP errors | High Impact | 8
25 | 2 | Drop bids | Dropped bids are reflected in database. However, bids are not updated in UI | Low impact | 4
26 | 2 | Add Bids | Able to bid for cause with pre-requisite | Low impact | 3
27 | 2 | Database | Database crash as data on course and section are duplicated | Critical Impact | 15
28 | 3 | Add Bids | Able to add bid(s) for other schools at round 1. | Low impact | 4 | 178 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
29 | 3 | Deployment | Testcase works locally however produces error on AWS servers. | Low impact | 6
30 | 3 | Login page | PHP error in login page | Critical Impact | 13
31 | 3 | Rounds clearing logic | Round 2 Clearing logic into function not working as intended | High Impact | 10
32 | 3 | Rounds clearing logic | Bid’s vacancy limit is not being capture as round 1 opening is closed | Low impact | 3
33 | 3 | Add Bids | Redundancy double sort function through SQL retrieval and creating a function to retrieve course(s) | High impact | 12
34 | 3 | Rounds clearing logic | Duplicate data input in Round 1 Clearing logic | High Impact | 13
35 | 3 | Add Bids | When bidding for multiple courses, errors prompts does not differentiate which course and section is causing which error(s) | High Impact | 9
36 | 3 | Bootstrap (Upload) | Upload option disappears after round 1 | Low impact | 3
37 | 3 | Bootstrap (Upload) | Bootstrap validation logic error | Critical Impact | 15
38 | 3 | Rounds clearing logic | Round 1 opening bidding bug as e$ is not updated. | High Impact | 9
39 | 3 | Add Bids | Bid value is not a float but an integer. | High Impact | 8
40 | 3 | Admin Page | You have to refresh the page between windows when closing and opening rounds | High Impact | 10
41 | 3 | Bootstrap (Upload) | Blank screen appear after bootstrapping for the first time. Need to relogin again for the 'Round Open/Close' option to show. | Critical Impact | 12
42 | 3 | Bootstrap (Upload) | After bootstrapping, bid amount will always end up as whole number instead of a float value | High Impact | 10
43 | 3 | Add Bid | There is a frontend error where it does not allow users to input decimal places for the 'Add Bid' page | Critical Impact | 11
44 | 3 | Bootstrap (Upload) | Add bids instead of update bids when userid and current course exists, causing a exam timetable clash. Should be bid update instead. | Critical Impact | 18
45 | 3 | JSON - Round closing | Vacancy not updated between rounds | High Impact | 9
46 | 3 | JSON - Bootstrap | Error field message not sorted | Low impact | 3
47 | 4 | Bootstrap (Upload) | Bootstrap Validation Error | High Impact | 10 | 101 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
48 | 4 | Datebase & UI | e$ produce alphanumeric and long string values | High Impact | 10
49 | 4 | JSON | Unexpected values showing for JSON responses | Low impact | 3
50 | 4 | Rounds clearing logic | Round 2 logic error, results not displaying immediately upon bidding | High Impact | 8
51 | 4 | Databse | Issues with bid states within database | High Impact | 10
52 | 4 | Rounds clearing logic | Display PHP error at round 1 closing of viewing of bid results | Critical Impact | 11
53 | 4 | JSON | JSON tracker display error upon running JSON testcases | Low impact | 3
54 | 4 | Add Bid | There is an error caused by non-standardized variable names | Critical Impact | 13
55 | 4 | Add Bid | Vacancy does not change if a bid is dropped | Critical Impact | 11
56 | 4 | Add Bid | No validation if the vacancy is already at 0 - bid goes through even though there is no vacancy | High Impact | 10
57 | 4 | Add Bid | No validation if you bid for two sections of the same course at the same time | Low Impact | 1
58 | 4 | Add Bid | No validation if you bid for two sections of the same course in separate bids | Low Impact | 1
59 | 4 | Add Bid | Should be able to bid even when vacancy is temporarily 0 during round 2. Shouldn't allow bids if round 1 ends, and vacancy is 0 | High Impact | 8
60 | 4 | Drop Bid | You can drop a bid once the window is closed. You should only be able to drop bids during active rounds | Low Impact | 1
61 | 4 | Drop Section | You can drop a section once the window is closed. You should only be able to drop sections during active rounds | Low Impact | 1
62 | 5 | Bootstrap | Does not show success message or how many lines have been processed | Low Impact | 1 | 176 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
63 | 5 | Bootstrap | Non-consistent bid amounts when clicking on landing page and add bid page | High Impact | 10
64 | 5 | Landing page | Not being able to show status result of bids after round 1 | High Impact | 10
65 | 5 | Drop Section | Money should be refunded when a section is dropped | High Impact | 10
66 | 5 | Drop Bid round 2 | When vacancy reaches max limit, those that were out-bid would causes all other bids status to fail. | Critical Impact | 18
67 | 5 | Bootstrap | Bootstrap goes through even though no file is added | High Impact | 8
68 | 5 | Add bid page - process bids | PHP Error from empty bids during processing of bids. | Critical Impact | 12
69 | 5 | Admin Page | Exclamation mark appears if no file is imported on the admin page | Low Impact | 2
70 | 5 | Admin Page | Error if no file is imported on the bootstrap | Low impact | 2
71 | 5 | Add Bid page | Bid amount can exceed amount in wallet | High Impact | 8
72 | 5 | Deployment - Admin Page | White screen during round clearing in deployment | Critical Impact | 13
73 | 5 | Deployment - Backend | Unable to make the database changes when opening the second round | Critical Impact | 15
74 | 5 | Deployment - Landing Page | Bid status unable to change during after round 1 closing | Critical Impact | 16
75 | 5 | Deployment - Drop bid page | In round 2 you can drop the bid multiple times and that amount will still be added to the student's wallet | Critical Impact | 17
76 | 5 | Deployment - Backend | Integrity error as the data is inserted twice | Critical Impact | 12
77 | 5 | Add bid page | Time filter not working properly if timings of classes on bootstrap changes | High Impact | 9
78 | 5 | Deployment - Drop Bid | Bid is dropped on the front end, but when refreshed will come back; not updated on the database | Critical Impact | 13

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User) | PHP Error accompanied with error prompt, which is design to inform the user about the error. | Resolved | 2019-09-30 | 2019-10-01 | Sheng Qin & Vittorio
2 | 1 | Login (Admin) | Password accepted for both capitalised and non capitalised variations | Resolved | 2019-09-30 | 2019-10-01 | Sheng Qin & Vittorio
3 | 1 | Bootstrap (Upload) | Error at the following CSV file: Course.csv - AT Row 2 - UNDER Exam Date Column with (empty Exam Date) which a cause PHP error. | Resolved | 2019-10-01 | 2019-10-09 | Sheng Qin & Vittorio
4 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 3 - UNDER Exam Date Column with (Alphanumeric exam date) - Alphanumeric exam date will cause PHP error. | Resolved | 2019-10-01 | 2019-10-09 | Sheng Qin & Vittorio
5 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 4 - UNDER Exam Date Column with (Exam Date space) - Date with space will cause PHP error. | Resolved | 2019-10-01 | 2019-10-09 | Sheng Qin & Vittorio
6 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 5 - UNDER Exam Date Column with (Date with extra numbers) - Date with extra numbers will cause PHP error | Resolved | 2019-10-01 | 2019-10-09 | Sheng Qin & Vittorio
7 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 15 - UNDER Title Column with (empty title) - data could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-09 | Brendon & DaEun
8 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 16 - UNDER Description Column with (Empty description) - deleted description will cause PHP error | Resolved | 2019-10-01 | 2019-10-09 | Brendon & DaEun
9 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 18 - UNDER Course Column with (Empty course) - Data could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-09 | Brendon & DaEun
10 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 22 - UNDER School Column with (Empty School) - Date could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-09 | Brendon & DaEun
11 | 2 | Bootstrap (Upload) | This page isn’t working. 18.216.225.229 is currently unable to handle this request. A row with duplicate course AND section in section.csv will result in this error. | Resolved | 2019-10-09 | 2019-10-09 | Sheng Qin & DaEun
12 | 2 | Bootstrap (Upload) | When course.csv has all empty fields for all columns in a row, it only shows "blank course" . The line number does not increase, causing subsequent errors to have a wrong line number (smaller by 1) | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
13 | 2 | Bootstrap (Upload) | Bootstrap error result in PHP error causes by Database due to incorrect column type | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
14 | 2 | Bootstrap (Upload) | Bid.csv cause PHP error upon bootstrap upload | Resolved | 2019-10-09 | 2019-10-09 | Vittorio, Sheng Qin & DaEun
15 | 2 | Drop bids | dropped bids were not removed | Resolved | 2019-10-09 | 2019-10-09 | Vittorio, Sheng Qin & DaEun
16 | 2 | Landing page | Current bid is displayed as php error | Resolved | 2019-10-09 | 2019-10-09 | Vittorio, Sheng Qin & DaEun
17 | 2 | add bids | Above 5 bids cause PHP error | Resolved | 2019-10-09 | 2019-10-10 | Vittorio, Sheng Qin & DaEun
18 | 2 | Admin Page | Upon logging into admin page, PHP error is produce and unable to bootstrap. | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
19 | 2 | Rounds clearing logic | Upon closing "round 1 opening" after bootstrap, cause PHP error and does not reflect on rounds in landing page. | Resolved | 2019-10-09 | 2019-10-15 | Matthew and Brendon
20 | 2 | Landing page | Landing page does not show what round the user is in | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
21 | 2 | Landing page | landing page does not show what the status of the round is | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
22 | 2 | Landing page / add bids | Bid value does not get deducted upon adding bids | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
23 | 2 | bids | Bid value can be come negative value | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
24 | 2 | Landing Page / bids | Trying to show the e$ produce PHP errors | Resolved | 2019-10-10 | 2019-10-10 | Vittorio, Sheng Qin & DaEun
25 | 2 | Drop bids | Drop bids is reflect in database, however bids and e$ are still refelcted in UI | Resolved | 2019-10-10 | 2019-10-10 | Vittorio, Sheng Qin & DaEun
26 | 2 | Add Bids | Able to bid for cause with pre-requisite | Resolved | 2019-10-10 | 2019-10-10 | Vittorio, Sheng Qin & DaEun
27 | 2 | Databse | Database crash as data on course and section are duplicated | Resolved | 2019-10-16 | 2019-10-16 | Vittorio, Sheng Qin & DaEun
28 | 3 | Add Bids | Able to add bid(s) for other schools at round 1. | Resolved | 2019-10-16 | 2019-10-16 | Sheng Qin & Brendon
29 | 3 | Deployment | Testcase works locally however produce error on AWS servers. | Resolved | 2019-10-16 | 2019-10-16 | Sheng Qin & Brendon
30 | 3 | Login page | PHP error in login page | Resolved | 2019-10-16 | 2019-10-16 | Sheng Qin & Brendon
31 | 3 | Rounds clearing logic | Round 2 Clearing logic into function not working as intended | Resolved | 2019-10-19 | 2019-10-27 | Vittorio, Sheng Qin & DaEun
32 | 3 | Rounds clearing logic | Bid’s vacancy limit is not being capture as round 1 opening is closed | Resolved | 2019-10-20 | 2019-10-28 | Matthew & Vittorio
33 | 3 | Add Bids | Redundancy double sort function through SQL retrieval and creating a function to retrieve course(s) | Resolved | 2019-10-20 | 2019-10-20 | Matthew & Vittorio
34 | 3 | Rounds clearing logic | Duplicate data input in Round 1 Clearing logic | Resolved | 2019-10-20 | 2019-10-27 | Matthew & Vittorio
35 | 3 | Add Bids | When bidding for multiple courses, errors prompts does not differentiate which course and section is causing which error(s) | Resolved | 2019-10-28 | 2019-10-28 | Sheng Qin & Brendon
36 | 3 | Bootstrap (Upload) | Upload option disappears after round 1 | Resolved | 2019-10-28 | 2019-10-28 | Sheng Qin & Brendon
37 | 3 | Bootstrap (Upload) | Boostrap validation logic error | Resolved | 2019-10-29 | 2019-10-29 | Matthew & Vittorio
38 | 3 | Rounds clearing logic | Round 1 opening bidding bug as e$ is not updated. | Resolved | 2019-10-29 | 2019-10-29 | Matthew & Vittorio
39 | 3 | Add Bids | Bid value is not a float but an integer. | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Vittorio
40 | 3 | Admin Page | You have to refresh the page between windows when closing and opening rounds | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Vittorio
41 | 3 | Bootstrap (Upload) | Blank screen appear after bootstrapping for the first time. Need to relogin again for the 'Round Open/Close' option to show. | Resolved | 2019-10-31 | 2019-11-02 | Sheng Qin & Brendon
42 | 3 | Bootstrap (Upload) | After bootstrapping, bid amount will always end up as whole number instead of a float value | Resolved | 2019-10-31 | 2019-11-02 | Sheng Qin & Brendon
43 | 3 | Add Bid | There is a frontend error where it does not allow users to input decimal places for the 'Add Bid' page | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Vittorio
44 | 3 | Bootstrap (Upload) | Add bids instead of update bids when userid and current course exists, causing a exam timetable clash. Should be bid update instead. | Resolved | 2019-10-31 | 2019-11-02 | Sheng Qin & Brendon
45 | 3 | JSON - Round closing | Vacancy not updated between rounds | Resolved | 2019-10-31 | 2019-11-02 | Sheng Qin & Brendon
46 | 3 | JSON - Bootstrap | Error field message not sorted | Resolved | 2019-10-31 | 2019-11-02 | Sheng Qin & Brendon
47 | 4 | Bootstrap (Upload) | Bootstrap Validation Error | Resolved | 2019-11-05 | 2019-11-05 | Vittorio & DaEun
48 | 4 | Datebase & UI | e$ produce alphanumeric and long string values | Resolved | 2019-11-05 | 2019-11-05 | Vittorio & DaEun
49 | 4 | JSON | Unexpected values showing for JSON responses | Resolved | 2019-11-05 | 2019-11-08 | Matthew & Sheng Qin
50 | 4 | Rounds clearing logic | Round 2 logic error, results not displaying immediately upon bidding | Resolved | 2019-11-05 | 2019-11-08 | Matthew & Sheng Qin
51 | 4 | Databse | Issues with bid states within database | Resolved | 2019-11-05 | 2019-11-08 | Vittorio & DaEun
52 | 4 | Rounds clearing logic | Display PHP error at round 1 closing of viewing of bid results | Resolved | 2019-11-05 | 2019-11-08 | Vittorio & DaEun
53 | 4 | JSON | JSON tracker display error upon running JSON testcases | Resolved | 2019-11-05 | 2019-11-08 | Matthew & Sheng Qin
54 | 4 | Add Bid | There is an error caused by non-standardized variable names | Resolved | 2019-11-09 | 2019-11-09 | Matthew & Sheng Qin
55 | 4 | Add Bid | Vacancy does not change if a bid is dropped | Resolved | 2019-11-09 | 2019-11-09 | Matthew & Sheng Qin
56 | 4 | Add Bid | No validation if the vacancy is already at 0 - bid goes through even though there is no vacancy | Resolved | 2019-11-09 | 2019-11-09 | Matthew & Sheng Qin
57 | 4 | Add Bid | No validation if you bid for two sections of the same course at the same time | Resolved | 2019-11-09 | 2019-11-09 | Matthew & Sheng Qin
58 | 4 | Add Bid | No validation if you bid for two sections of the same course in separate bids | Resolved | 2019-11-09 | 2019-11-09 | Matthew & Sheng Qin
59 | 4 | Add Bid | Should be able to bid even when vacancy is temporarily 0 during round 2. Shouldn't allow bids if round 1 ends, and vacancy is 0 | Resolved | 2019-11-09 | 2019-11-09 | Vittorio & DaEun
60 | 4 | Drop Bid | You can drop a bid once the window is closed. You should only be able to drop bids during active rounds | Resolved | 2019-11-11 | 2019-11-11 | Matthew & Sheng Qin
61 | 4 | Drop Section | You can drop a section once the window is closed. You should only be able to drop sections during active rounds | Resolved | 2019-11-11 | 2019-11-11 | Matthew & Sheng Qin
62 | 5 | Bootstrap | Does not show success message or how many lines have been processed | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
63 | 5 | Bootstrap | Non-consistent bid amounts when clicking on landing page and add bid page | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
64 | 5 | Landing page | Not being able to show status result of bids after round 1 | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
65 | 5 | Drop Section | Money should be refunded when a section is dropped | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
66 | 5 | Drop Bid round 2 | When vacancy reaches max limit, those that were out-bid would causes all other bids status to fail. | Resolved | 14/11/2019 | 14/11/2019 | Brendon & Vittorio
67 | 5 | Bootstrap | Bootstrap goes through even though no file is added | Resolved | 14/11/2019 | 14/11/2019 | Brendon & Vittorio
68 | 5 | Add bid page - process bids | PHP Error from empty bids during processing of bids. | Resolved | 14/11/2019 | 14/11/2019 | Brendon & Vittorio
69 | 5 | Admin Page | Exclamation mark appears if no file is imported on the admin page | Resolved | 15/11/2019 | 15/11/2019 | Matthew & DaEun
70 | 5 | Admin Page | Error if no file is imported on the bootstrap | Resolved | 15/11/2019 | 15/11/2019 | Matthew & DaEun
71 | 5 | Add Bid page | Bid amount can exceed amount in wallet | Resolved | 15/11/2019 | 15/11/2019 | Brendon & Vittorio
72 | 5 | Deployment - Admin Page | White screen during round clearing in deployment | Resolved | 15/11/2019 | 15/11/2019 | Brendon & Vittorio
73 | 5 | Deployment - Backend | Unable to make the database changes when opening the second round | Resolved | 15/11/2019 | 15/11/2019 | Brendon & Vittorio
74 | 5 | Deployment - Landing Page | Bid status unable to change during after round 1 closing | Resolved | 15/11/2019 | 15/11/2019 | Brendon & Vittorio
75 | 5 | Deployment - Drop bid page | In round 2 you can drop the bid multiple times and that amount will still be added to the student's wallet | Resolved | 15/11/2019 | 15/11/2019 | Brendon & Vittorio
76 | 5 | Deployment - Backend | Integrity error as the data is inserted twice | Resolved | 15/11/2019 | 15/11/2019 | Matthew & DaEun
77 | 5 | Add bid page | Time filter not working properly if timings of classes on bootstrap changes | Resolved | 15/11/2019 | 15/11/2019 | Matthew & DaEun
78 | 5 | Deployment - Drop Bid | Bid is dropped on the front end, but when refreshed will come back; not updated on the database | Resolved | 15/11/2019 | 15/11/2019 | Matthew & DaEun