## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | PHP Error accompanied with error prompt, which is design to inform the user about the error. | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing.
2 | 1 | Bootstrap (Upload) | Error at the following CSV file: Course.csv - AT Row 2 - UNDER Exam Date Column with (empty Exam Date) which a cause PHP error. | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
3 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 3 - UNDER Exam Date Column with (Alphanumeric exam date) - Alphanumeric exam date will cause PHP error. | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
4 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 4 - UNDER Exam Date Column with (Exam Date space) - Date with space will cause PHP error. | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
5 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 5 - UNDER Exam Date Column with (Date with extra numbers) - Date with extra numbers will cause PHP error | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
6 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 15 - UNDER Title Column with (empty title) - data could pass through, when field should not allow empty variables | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
7 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 16 - UNDER Description Column with (Empty description) - deleted description will cause PHP error | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
8 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 18 - UNDER Course Column with (Empty course) - Data could pass through, when field should not allow empty variables | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
9 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 22 - UNDER School Column with (Empty School) - Date could pass through, when field should not allow empty variables | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
10 | 2 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 23 - UNDER Exam Date Column with (Alphanumeric)-Alphanumeric exam date will give a PHP error | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
11 | 2 | Bootstrap (Upload) | When course.csv has all empty fields for all columns in a row, it only shows "blank course" . The line number does not increase, causing subsequent errors to have a wrong line number (smaller by 1) | Low impact | 1 |  | Continue with current schedule development, Project Manager reschedule a session for bug fixing. Impact not deem as high due to initial phase and bootstrap validation is under implementing
| 2 | Bootstrap (Upload) | Bootstrap error result in PHP error causes by Database due to incorrect column type | Critical Impact
| 2 | Bootstrap (Upload) | Bid.csv cause PHP error upon bootstrap upload | Critical Impact
| 2 | drop bids | dropped bids were not removed | Low impact
| 2 | Landing page | current bid is displayed as php error | Low impact
| 2 | add bids | Above 5 bids cause PHP error | Low impact
| 2 | Admin Page | Upon logging into admin page, PHP error is produce and unable to bootstrap. | Critical Impact
| 2 | Rounds clearing logic | Upon closing "round 1 opening" after bootstrap, cause PHP error and does not reflect on rounds in landing page. | Low impact
12 | 2 | Landing page | User unable to determine which round they are in | High Impact
14 | 2 | Landing page | User unable to determine whether the round is open or not | High Impact
| 2 | Landing page / add bids | Bid value does not get deducted upon adding bids
| 2 | bids | Bid value can be come negative value
| 2 | Landing Page / bids | e$ prdce PHP errors
| 2 | Drop bids | Dropped bids are reflect in database, however bids are not updated in UI
| 2 | Add Bids | Able to bid for cause with pre-requisite
| 2 | Databse | Database crash as data on course and section are duplicated
| 3 | Add Bids | Able to add bid(s) for other schools at round 1.
| 3 | Deployment | Testcase works locally however produce error on AWS servers.
| 3 | Add Bids | Bid value is not a float but an integer.
3 | 3 | Admin Page | You have to refresh the page between windows when closing and opening rounds | High Impact
13 | 3 | Bootstrap (Upload) | Blank screen appear after bootstrapping for the first time. Need to relogin again for the 'Round Open/Close' option to show. | Critical Impact
14 | 3 | Bootstrap (Upload) | After bootstrapping, bid amount will always end up as whole number instead of a float value | High Impact
15 | 3 | Add Bid | There is a frontend error where it does not allow users to input decimal places for the 'Add Bid' page | High Impact
16 | 3 | Bootstrap (Upload) | Add bids instead of update bids when userid and current course exists, causing a exam timetable clash. Should be bid update instead. | Critical Impact
17 | 3 | JSON - Bootstrap | Error field message not sorted | Low impact
18 | 3 | Add Bid | There is an error caused by non-standardized variable names | High Impact
19 | 3 | Add Bid | Vacancy does not change if a bid is dropped | Critical Impact
20 | 3 | Add Bid | No validation if the vacancy is already at 0 - bid goes through even though there is no vacancy | High Impact
21 | 3 | Add Bid | No validation if you bid for two sections of the same course at the same time | Low Impact
22 | 3 | Add Bid | No validation if you bid for two sections of the same course in separate bids | Low Impact
23 | 3 | Add Bid | Should be able to bid even when vacancy is temporarily 0 during round 2. Shouldn't allow bids if round 1 ends, and vacancy is 0 | High Impact
24 | 3 | Drop Bid | You can drop a bid once the window is closed. You should only be able to drop bids during active rounds | Low Impact
25 | 3 | Drop Section | You can drop a section once the window is closed. You should only be able to drop sections during active rounds | Low Impact
26 | 5 | Bootstrap | Does not show success message or how many lines have been processed | Low Impact
27 | 5 | Bootstrap | Non-consistent bid amounts when clicking on landing page and add bid page | High Impact
28 | 5 | Landing page | Not being able to show status result of bids after round 1 | High Impact
29 | 5 | Drop Section | Money should be refunded when a section is dropped | High Impact
30 | 5 | Drop Bid round 2 | When vacancy reaches max limit, those that were out-bid would causes all other bids status to fail. | Critical Impact
| 5 | Bootstrap | Able bootstrap without importing bootstrap files
| 5 | Add bid page - process bids | PHP Error from empty bids during processing of bids.
31 | 5 | Admin Page | Exclamation mark appears if no file is imported on the admin page | Low Impact
32 | 5 | Admin Page | Error if no file is imported on the bootstrap | Low impact
| 5 | Add Bid page | Bid amount can exceed amount in wallet

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User) | PHP Error accompanied with error prompt, which is design to inform the user about the error. | Resolved | 2019-09-30 | 2019-10-01 | Sheng Qin & Vittorio
2 | 1 | Bootstrap (Upload) | Error at the following CSV file: Course.csv - AT Row 2 - UNDER Exam Date Column with (empty Exam Date) which a cause PHP error. | Resolved | 2019-10-01 | 2019-10-09 | Sheng Qin & Vittorio
3 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 3 - UNDER Exam Date Column with (Alphanumeric exam date) - Alphanumeric exam date will cause PHP error. | Resolved | 2019-10-01 | 2019-10-09 | Sheng Qin & Vittorio
4 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 4 - UNDER Exam Date Column with (Exam Date space) - Date with space will cause PHP error. | Resolved | 2019-10-01 | 2019-10-09 | Sheng Qin & Vittorio
5 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 5 - UNDER Exam Date Column with (Date with extra numbers) - Date with extra numbers will cause PHP error | Resolved | 2019-10-01 | 2019-10-09 | Sheng Qin & Vittorio
6 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 15 - UNDER Title Column with (empty title) - data could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-09 | Brendon & DaEun
7 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 16 - UNDER Description Column with (Empty description) - deleted description will cause PHP error | Resolved | 2019-10-01 | 2019-10-09 | Brendon & DaEun
8 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 18 - UNDER Course Column with (Empty course) - Data could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-09 | Brendon & DaEun
9 | 1 | Bootstrap (Upload) | Error at the following CSV file Course.csv - AT Row 22 - UNDER School Column with (Empty School) - Date could pass through, when field should not allow empty variables | Resolved | 2019-10-01 | 2019-10-09 | Brendon & DaEun
10 | 2 | Bootstrap (Upload) | This page isn’t working. 18.216.225.229 is currently unable to handle this request. A row with duplicate course AND section in section.csv will result in this error. | Resolved | 2019-10-09 | 2019-10-09 | Sheng Qin & DaEun
11 | 2 | Bootstrap (Upload) | When course.csv has all empty fields for all columns in a row, it only shows "blank course" . The line number does not increase, causing subsequent errors to have a wrong line number (smaller by 1) | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
| 2 | Bootstrap (Upload) | Bootstrap error result in PHP error causes by Database due to incorrect column type | Resloved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
| 2 | Bootstrap (Upload) | Bid.csv cause PHP error upon bootstrap upload | Resloved | 2019-10-09 | 2019-10-09 | Vittorio, Sheng Qin & DaEun
| 2 | drop bids | dropped bids were not removed | Resloved | 2019-10-09 | 2019-10-09 | Vittorio, Sheng Qin & DaEun
| 2 | Landing page | current bid is displayed as php error | Resloved | 2019-10-09 | 2019-10-09 | Vittorio, Sheng Qin & DaEun
| 2 | add bids | Above 5 bids cause PHP error | Resloved | 2019-10-09 | 2019-10-10 | Vittorio, Sheng Qin & DaEun
|  | Admin Page | Upon logging into admin page, PHP error is produce and unable to bootstrap. | Resloved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
|  | Rounds clearing logic | Upon closing "round 1 opening" after bootstrap, cause PHP error and does not reflect on rounds in landing page. | Resloved | 2019-10-09 | 2019-10-15 | Matthew and Brendon
12 | 2 | Landing page | Landing page does not show what round the user is in | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
13 | 2 | Landing page | landing page does not show what the status of the round is | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
| 2 | Landing page / add bids | Bid value does not get deducted upon adding bids | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
| 2 | bids | Bid value can be come negative value | Resolved | 2019-10-09 | 2019-10-09 | Matthew and Brendon
| 2 | Landing Page / bids | e$ prdce PHP errors | Resolved | 2019-10-10 | 2019-10-10 | Vittorio, Sheng Qin & DaEun
| 2 | Drop bids | Drop bids is reflect in database, however bids and e$ are still refelcted in UI | Reseloved | 2019-10-10 | 2019-10-10 | Vittorio, Sheng Qin & DaEun
| 2 | Add Bids | Able to bid for cause with pre-requisite | Reseloved | 2019-10-10 | 2019-10-10 | Vittorio, Sheng Qin & DaEun
| 2 | Databse | Database crash as data on course and section are duplicated |  | 2019-10-16 | 2019-10-16 | Vittorio, Sheng Qin & DaEun
| 3 | Add Bids | Able to add bid(s) for other schools at round 1. | Reseloved
| 3 | Deployment | Testcase works locally however produce error on AWS servers. | Reseloved
| 3 | Add Bids | Bid value is not a float but an integer. | Resolved | 2019-10-31 | 2019-11-02 | Vittorio & DaEun
| 3 | Admin Page | You have to refresh the page between windows when closing and opening rounds | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Sheng Qin
14 | 3 | Bootstrap (Upload) | Blank screen appear after bootstrapping for the first time. Need to relogin again for the 'Round Open/Close' option to show. | Resolved | 2019-10-31 | 2019-11-02 | Sheng Qin & Brendon
15 | 3 | Bootstrap (Upload) | After bootstrapping, bid amount will always end up as whole number instead of a float value | Resolved | 2019-10-31 | 2019-11-02 | Sheng Qin & Brendon
16 | 3 | Add Bid | There is a frontend error where it does not allow users to input decimal places for the 'Add Bid' page | Resolved | 2019-10-31 | 2019-11-02 | Matthew & Vittorio
17 | 3 | Bootstrap (Upload) | Add bids instead of update bids when userid and current course exists, causing a exam timetable clash. Should be bid update instead. | Resolved | 2019-10-31 | 2019-11-02 | Sheng Qin & Brendon
18 | 3 | JSON - Bootstrap | Error field message not sorted | Resolved | 2019-10-31 | 2019-11-02 | Sheng Qin & Brendon
19 | 4 | Add Bid | There is an error caused by non-standardized variable names | Resolved | 2019-11-07 | 2019-11-07 | Matthew & Sheng Qin
20 | 4 | Add Bid | Vacancy does not change if a bid is dropped | Resolved | 2019-11-07 | 2019-11-07 | Matthew & Sheng Qin
21 | 4 | Add Bid | No validation if the vacancy is already at 0 - bid goes through even though there is no vacancy | Resolved | 2019-11-07 | 2019-11-07 | Matthew & Sheng Qin
22 | 4 | Add Bid | No validation if you bid for two sections of the same course at the same time | Resolved | 2019-11-09 | 2019-11-09 | Matthew & Sheng Qin
23 | 4 | Add Bid | No validation if you bid for two sections of the same course in separate bids | Resolved | 2019-11-09 | 2019-11-11 | Matthew & Sheng Qin
24 | 4 | Add Bid | Should be able to bid even when vacancy is temporarily 0 during round 2. Shouldn't allow bids if round 1 ends, and vacancy is 0 | Resolved | 2019-11-09 | 2019-11-09 | Vittorio & DaEun
25 | 4 | Drop Bid | You can drop a bid once the window is closed. You should only be able to drop bids during active rounds | Resolved | 2019-11-11 | 2019-11-11 | Matthew & Sheng Qin
26 | 4 | Drop Section | You can drop a section once the window is closed. You should only be able to drop sections during active rounds | Resolved | 2019-11-11 | 2019-11-11 | Matthew & Sheng Qin
27 | 5 | Bootstrap | Does not show success message or how many lines have been processed | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
28 | 5 | Bootstrap | Non-consistent bid amounts when clicking on landing page and add bid page | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
29 | 5 | Landing page | Not being able to show status result of bids after round 1 | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
30 | 5 | Drop Section | Money should be refunded when a section is dropped | Resolved | 14/11/2019 | 14/11/2019 | Matthew & DaEun
31 | 5 | Drop Bid round 2 | When vacancy reaches max limit, those that were out-bid would causes all other bids status to fail. | Resolved | 14/11/2019 | 14/11/2019 | Brendon & Vittorio
32 | 5 | Bootstrap | Able bootstrap without importing bootstrap files | Resolved | 14/11/2019 | 14/11/2019 | Brendon & Vittorio
33 | 5 | Add bid page - process bids | PHP Error from empty bids during processing of bids. | Resolved | 14/11/2019 | 14/11/2019 | Brendon & Vittorio
34 | 5 | Admin Page | Exclamation mark appears if no file is imported on the admin page | Resolved | 16/11/2019 | 16/11/2019 | Matthew & DaEun
35 | 5 | Admin Page | Error if no file is imported on the bootstrap | Resolved | 16/11/2019 | 16/11/2019 | Matthew & DaEun
36 | 5 | Add Bid page | Bid amount can exceed amount in wallet | Resolved | 16/11/2019 | 16/11/2019 | Brendon & Vittorio
37