## Week 5
Person | Question | Week: 16/09/2019 to 20/09/2019 | [6 empty] | Person | Question | Week: 15/09/2019 to 21/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Matthew Tan | What did you do yesterday? |  |  |  |  | We had a weekly meeting, discussed next sprint. See minutes for more information | Not a work day | Not a work day | Matthew Tan | What did you do yesterday? | Not a work day | Not a work day | Did up scheduling with Brendon and Da Eun | Not a work day | Not a work day | Not a work day | Not a work day
| What will you do today? |  |  |  |  | Not a work day | Not a work day | Not a work day |  | What will you do today? | Not a work day | Did up scheduling with Brendon and Da Eun | Not a work day | Meeting with team. Refer to minutes for further details | Not a work day | Not a work day | Not a work day
| Do you have any obstacles? |  |  |  |  | Not a work day | Not a work day | Not a work day |  | Do you have any obstacles? | Not a work day | How to break down the task into smaller sub-tasks for the scheduling | NIL | NIL | Not a work day | Not a work day | Not a work day
Brendon Lim | What did you do yesterday? |  |  |  |  | Assisted Sheng Qin in the implementation code for the bid and landing page. Also attended weekly meeting | Not a work day | Not a work day | Brendon Lim | What did you do yesterday? | Not a work day | Not a work day | Did up scheduling with Matthew and Da Eun | Not a work day | Not a work day | Not a work day | Not a work day
| What will you work on today? |  |  |  |  | Not a work day | Not a work day | Not a work day |  | What will you work on today? | Not a work day | Did up scheduling with Matthew and Da Eun | Not a work day | Meeting with team. Refer to minutes for further details | Not a work day | Not a work day | Not a work day
| Do you have any obstacles? |  |  |  |  | Not a work day | Not a work day | Not a work day |  | Do you have any obstacles? | Not a work day | Breaking down tasks for scheduling | NIL | NIL | Not a work day | Not a work day | Not a work day
Cha Daeun | What did you do yesterday? |  |  |  |  | We had a weekly meeting, discussed next sprint. See minutes for more information | Not a work day | Not a work day | Cha Daeun | What did you do yesterday? | Not a work day | Not a work day | Did up scheduling with Matthew and Brendon, made template slides for presentation | Not a work day | Not a work day | Not a work day | Not a work day
| What will you work on today? |  |  |  |  | Not a work day | Not a work day | Not a work day |  | What will you work on today? | Not a work day | Did up scheduling with Matthew and Brendon, made template slides for presentation | Not a work day | Meeting with team. Refer to minutes for further details | Not a work day | Not a work day | Not a work day
| Do you have any obstacles? |  |  |  |  | Not a work day | Not a work day | Not a work day |  | Do you have any obstacles? | Not a work day | NIL | NIL | NIL | Not a work day | Not a work day | Not a work day
Vittorio Carecci | What did you do yesterday? |  |  |  |  | We had a weekly meeting, discussed next sprint. See minutes for more information | Not a work day | Not a work day | Vittorio Carecci | What did you do yesterday? | Not a work day | Not a work day | Pair programming with Sheng Qin. Updated 'add bid page process' page and 'add big' page | Not a work day | Not a work day | Not a work day | Not a work day
| What will you work on today? |  |  |  |  | Working on updating the wireframe for extra pages and updating designs on the wireframe. | Not a work day | Not a work day |  | What will you work on today? | Not a work day | Pair programming with Sheng Qin. Updated 'add bid page process' page and 'add big' page | Not a work day | Meeting with team. Refer to minutes for further details | Not a work day | Not a work day | Not a work day
| Do you have any obstacles? |  |  |  |  | Trying to ensure that he maintains concentration | Not a work day | Not a work day |  | Do you have any obstacles? | Not a work day | NIL | NIL | NIL | Not a work day | Not a work day | Not a work day
Sheng Qin | What did you do yesterday? |  |  |  |  | Implemented code for the bid and landing page. Also attended the meeting | Not a work day | Not a work day | Sheng Qin | What did you do yesterday? | Not a work day | Not a work day | Pair programming with Vittorio. Updated 'add bid page process' page and 'add big' page | Not a work day | Not a work day | Not a work day | Not a work day
| What will you work on today? |  |  |  |  | Not a work day | Not a work day | Not a work day |  | What will you work on today? | Not a work day | Pair programming with Vittorio. Updated 'add bid page process' page and 'add big' page | Not a work day | Not a work day | Not a work day | Not a work day | Not a work day
| Do you have any obstacles? |  |  |  |  | Not a work day | Not a work day | Not a work day |  | Do you have any obstacles? | Not a work day | NIL | NIL | NIL | Not a work day | Not a work day | Not a work day

## Week 6
Person | Question | Question | Week: 22/09/2019 to 28/09/2019
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Matthew Tan | What did you do yesterday? | What did you do yesterday? | Not a work day | Not a work day | Did up scheduling with Brendon and Da Eun | Not a work day | Not a work day | Updated slides in preparation for PM Review | Not a work day
| What will you do today? | What will you do today? | Not a work day | Did up scheduling with Brendon and Da Eun | Not a work day | Meeting with team. Refer to minutes for further details | Updated slides in preparation for PM Review | Updated slides in preparation for PM Review | Not a work day
| Do you have any obstacles? | Do you have any obstacles? | Not a work day | How to break down the task into smaller sub-tasks for the scheduling | NIL | NIL | Trying to figure out functionality requirements of the scheduling | Reconfiguring the functionality requirements for the scheduling | Not a work day
Brendon Lim | What did you do yesterday? | What did you do yesterday? | Not a work day | Not a work day | Did up scheduling with Matthew and Da Eun | Not a work day | Not a work day | Not a work day | Started on coding the bootstrap validation implementation
| What will you work on today? | What will you work on today? | Not a work day | Did up scheduling with Matthew and Da Eun | Not a work day | Meeting with team. Refer to minutes for further details | Not a work day | Started on coding the bootstrap validation implementation | Continued coding the boostrap validation implementation
| Do you have any obstacles? | Do you have any obstacles? | Not a work day | Breaking down tasks for scheduling | NIL | NIL | Not a work day | Figuring out how to implement logic validation | Figuring out how to implement logic validation
Cha Daeun | What did you do yesterday? | What did you do yesterday? | Not a work day | Not a work day | Did up scheduling with Matthew and Brendon, made template slides for presentation | Not a work day | Not a work day | Not a work day | Started on coding the bootstrap validation implementation
| What will you work on today? | What will you work on today? | Not a work day | Did up scheduling with Matthew and Brendon, made template slides for presentation | Not a work day | Meeting with team. Refer to minutes for further details | Not a work day | Started on coding the bootstrap validation implementation | Continued coding the boostrap validation implementation
| Do you have any obstacles? | Do you have any obstacles? | Not a work day | NIL | NIL | NIL | Not a work day | Figuring out how to implement logic validation | Figuring out how to implement logic validation
Vittorio Carecci | What did you do yesterday? | What did you do yesterday? | Not a work day | Not a work day | Pair programming with Sheng Qin. Updated 'add bid page process' page and 'add big' page | Not a work day | Not a work day | Not a work day | Started on coding the bootstrap validation implementation
| What will you work on today? | What will you work on today? | Not a work day | Pair programming with Sheng Qin. Updated 'add bid page process' page and 'add big' page | Not a work day | Meeting with team. Refer to minutes for further details | Not a work day | Started on coding the bootstrap validation implementation | Continued coding the boostrap validation implementation
| Do you have any obstacles? | Do you have any obstacles? | Not a work day | NIL | NIL | NIL | Not a work day | Figuring out how to implement logic validation | Figuring out how to implement logic validation
Sheng Qin | What did you do yesterday? | What did you do yesterday? | Not a work day | Not a work day | Pair programming with Vittorio. Updated 'add bid page process' page and 'add big' page | Not a work day | Not a work day | Not a work day | Started on coding the bootstrap validation implementation
| What will you work on today? | What will you work on today? | Not a work day | Pair programming with Vittorio. Updated 'add bid page process' page and 'add big' page | Not a work day | Not a work day | Not a work day | Started on coding the bootstrap validation implementation | Continued coding the boostrap validation implementation
| Do you have any obstacles? | Do you have any obstacles? | Not a work day | NIL | NIL | NIL | Not a work day | Figuring out how to implement logic validation | Figuring out how to implement logic validation

## Week 7
Person | Question | Week: 29/09/2019 to 05/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Matthew Tan | What did you do yesterday? | Not a work day | Conducted a meeting with the team. See minutes for more details | Not a working day | Not a working day | Team Meeting. Refer to minutes for more details | Not a working day | Not a working day
| What will you do today? | Conducted a meeting with the team. See minutes for more details | Re-edited the slides and assisted the team with bug metrics and validations | Not a working day | Team Meeting. Refer to minutes for more details | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | No time | Not a working day | NIL | Not a working day | Not a working day | Not a working day
Brendon Lim | What did you do yesterday? | Continued coding the boostrap validation implementation | Met with the team for a meeting. Continued coding the bootstrap validation implementation | Spent time doing bug metrics and validations with the rest of the team | Did validations. | Team Meeting. Refer to minutes for more details & redirect login page for admin | Not a working day | Not a working day
| What will you work on today? | Met with the team for a meeting. Continued coding the bootstrap validation implementation | Spent time doing bug metrics and validations with the rest of the team | Did validations, not finalised | Team Meeting. Refer to minutes for more details & redirect login page for admin | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | Finding the logic for bootstrap validation | Time issues | NIL | NIL | Not a working day | Not a working day | Not a working day
Cha Daeun | What did you do yesterday? | Continued coding the boostrap validation implementation | ppt slides for presentation and meeting | Not a working day | Not a working day | Team Meeting. Refer to minutes for more details & redirect login page for admin | Not a working day | Not a working day
| What will you work on today? | Met with the team for a meeting. Continued coding the bootstrap validation implementation | Not a working day | Not a working day | Team Meeting. Refer to minutes for more details & redirect login page for admin | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | Finding the logic for bootstrap validation | Not a working day | Not a working day | NIL | Not a working day | Not a working day | Not a working day
Vittorio Carecci | What did you do yesterday? | Continued coding the boostrap validation implementation | Met with the team for a meeting. Continued coding the bootstrap validation implementation | Bug metrics & Testcases | Not a working day | Team Meeting. Refer to minutes for more details | Not a working day | Not a working day
| What will you work on today? | Met with the team for a meeting. Continued coding the bootstrap validation implementation | Worked on bug metrics and validation with the team | Not a working day | Team Meeting. Refer to minutes for more details | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | Finding the logic for bootstrap validation | Just too many bugs to look through | PHP Errors, that do not highlight which row the error is from causing delay in test casing, thus resulting to individual row testing. | NIL | Not a working day | Not a working day | Not a working day
Sheng Qin | What did you do yesterday? | Continued coding the boostrap validation implementation | Coding the validations for bid.csv | Not a working day | Not a working day | Team Meeting. Refer to minutes for more details | Not a working day | Not a working day
| What will you work on today? | Met with the team for a meeting. Continued coding the bootstrap validation implementation | Finish up the validations for bid.csv and the common validations | Not a working day | Team Meeting. Refer to minutes for more details | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | Finding the logic for bootstrap validation | The complicated logic involved | Not a working day | NIL | Not a working day | Not a working day | Not a working day

## Week 8
Person | Question | Week: 6/10/2019 to 12/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Matthew Tan | What did you do yesterday? | Not a working day | Not a working day | Not a working day | (1)JSON APIs and functionality for Bootstrap, (2)Initiate round and active open and close round and (3) Drop bids | (1)JSON APIs and functionality for Bootstrap(continue) (2) Add Bid validation (3) Bootstrap validation | Not a working day | Drop bids
| What will you do today? | Not a working day | Not a working day | (1)JSON APIs and functionality for Bootstrap, (2)Initiate round and active open and close round and (3) Drop bids | (1)JSON APIs and functionality for Bootstrap(continue) (2) Add Bid validation (3) Bootstrap validation | Not a working day | Drop bids | Not a working day
| Do you have any obstacles? | Not a working day | Not a working day | Updates to SQL tables as data was not outputting correctly due to the column naming conversation | NIL | Not a working day | Programming logic for Notification dialogue box not executing. | Nil
Brendon Lim | What did you do yesterday? | Not a working day | Not a working day | Not a working day | (1)JSON APIs and functionality for Bootstrap, (2)Initiate round and active open and close round and (3) Drop bids | (1)JSON APIs and functionality for Bootstrap(continue) (2) Add Bid validation (3) Bootstrap validation | Not a working day | Drop bids
| What will you work on today? | Not a working day | Not a working day | (1)JSON APIs and functionality for Bootstrap, (2)Initiate round and active open and close round and (3) Drop bids | (1)JSON APIs and functionality for Bootstrap(continue) (2) Add Bid validation (3) Bootstrap validation | Not a working day | Drop bids | Not a working day
| Do you have any obstacles? | Not a working day | Not a working day | Updates to SQL tables as data was not outputting correctly due to the column naming conversation | NIL | Not a working day | Programming logic for Notification dialogue box not executing. | Nil
Cha Daeun | What did you do yesterday? | Not a working day | Not a working day | Not a working day | (1)Bootstrap validation | (1) Add Bid validation (2) Bootstrap validation | Not a working day | Not a working day
| What will you work on today? | Not a working day | Not a working day | (1)Bootstrap validation | (1) Add Bid validation (2) Bootstrap validation | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | Had difficulty retrieving data as output was none from a method from the bids table through the BidDAO’s retrieveStudentBidsWithInfo($userid) was resolve after an hour. | Bid had a Bug | Not a working day | Not a working day | Not a working day
Vittorio Carecci | What did you do yesterday? | Not a working day | Not a working day | Not a working day | (1)Updates and forecast on scheduling, (2)Breaking down of functionalities, (3)updates Team’s roles and responsibilities for next sprint, (4)Meeting agenda and minutes. | (1) Calculate critically path, (2) overall functionalities breakdown checklist and (3) update of schedule and forecasting. | (1) update of schedule and forecasting. | Drop bids
| What will you work on today? | Not a working day | Not a working day | (1)Updates and forecast on scheduling, (2)Breaking down of functionalities, (3)updates Team’s roles and responsibilities for next sprint, (4)Meeting agenda and minutes. | (1) Calculate critically path, (2) overall functionalities breakdown checklist and (3) update of schedule and forecasting. | (1) update of schedule and forecasting. | Drop bids | Not a working day
| Do you have any obstacles? | None | None | None | None | None | Programming logic for Notification dialogue box not executing. | Nil
Sheng Qin | What did you do yesterday? | Not a working day | Not a working day | Not a working day | (1)Bootstrap validation | (1) Add Bid validation (2) Bootstrap validation | Not a working day | Not a working day
| What will you work on today? | Not a working day | Not a working day | (1)Bootstrap validation | (1) Add Bid validation (2) Bootstrap validation | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | Had difficulty retrieving data as output was none from a method from the bids table through the BidDAO’s retrieveStudentBidsWithInfo($userid) was resolve after an hour. | Bid had a Bug | Not a working day | Not a working day | Not a working day

## Week 9
Person | Question | Week: 6/10/2019 to 12/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Matthew Tan | What did you do yesterday? | Not a working day | (1) Create static drop section page (2) Update Navigation Bar | (1) UI and Bootstrap design (2) Navigation Bar (3) Bids initiating of rounds round states, able to proceed from Initiate, round 1 and round 2 (4) Admins page, to show error when bootstrap is run.
| What will you do today? | (1) Create static drop section page (2) Update Navigation Bar | (1) UI and Bootstrap design (2) Navigation Bar (3) Bids initiating of rounds round states, able to proceed from Initiate, round 1 and round 2 (4) Admins page, to show error when bootstrap is run. | Testcases and Bug Metrics.
| Do you have any obstacles? | Nil | Several Issues with the logic as several codes were not output the desire response. | Discover bug within Bootstrap
Brendon Lim | What did you do yesterday? | Not a working day | (1) Create static drop section page (2) Update Navigation Bar | (1) UI and Bootstrap design (2) Navigation Bar (3) Bids initiating of rounds round states, able to proceed from Initiate, round 1 and round 2 (4) Admins page, to show error when bootstrap is run.
| What will you work on today? | (1) Create static drop section page (2) Update Navigation Bar | (1) UI and Bootstrap design (2) Navigation Bar (3) Bids initiating of rounds round states, able to proceed from Initiate, round 1 and round 2 (4) Admins page, to show error when bootstrap is run. | Testcases and Bug Metrics.
| Do you have any obstacles? | Nil | Several Issues with the logic as several codes were not output the desire response. | Discover bug within Bootstrap
Cha Daeun | What did you do yesterday? | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Not a working day | Testcases and Bug Metrics.
| Do you have any obstacles? | Not a working day | Not a working day | Discover bug within Bootstrap
Vittorio Carecci | What did you do yesterday? | Not a working day | (1) Create static drop section page (2) Update Navigation Bar | (1) UI and Bootstrap design (2) Navigation Bar (3) Bids initiating of rounds round states, able to proceed from Initiate, round 1 and round 2 (4) Admins page, to show error when bootstrap is run.
| What will you work on today? | (1) Create static drop section page (2) Update Navigation Bar | (1) UI and Bootstrap design (2) Navigation Bar (3) Bids initiating of rounds round states, able to proceed from Initiate, round 1 and round 2 (4) Admins page, to show error when bootstrap is run. | Preparation PowerPoint for Application Demo and online review
| Do you have any obstacles? | Nil | Several Issues with the logic as several codes were not output the desire response. | Nil
Sheng Qin | What did you do yesterday? | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Not a working day | Testcases and Bug Metrics.
| Do you have any obstacles? | Not a working day | Not a working day | Discover bug within Bootstrap